## PROJECT PARAMETERS
[Company Name]
Event Management Project Tracker
Company Confidential
Shaded cells are calculated for you. You do not need to enter anything into them.
PROJECT TYPE | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | Total
Event strategy development | 20% | 10% | 60% | 0% | 0% | 10% | 100%
Event planning | 20% | 50% | 10% | 10% | 0% | 10% | 100%
Event design | 20% | 20% | 0% | 50% | 0% | 10% | 100%
Event logistics | 20% | 60% | 0% | 0% | 10% | 10% | 100%
Event staffing | 20% | 10% | 0% | 0% | 60% | 10% | 100%
Event assessment | 20% | 20% | 20% | 20% | 0% | 20% | 100%
Blended rates | 180 | 120 | 150 | 100 | 80 | 60
| ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
PLANNED COST | 272340 | 319320 | 123450 | 106000 | 49320 | 53490
ACTUAL COST | 273960 | 324540 | 126150 | 104950 | 48160 | 53460
PLANNED HOURS | 1513 | 1774 | 685.8333 | 588.8889 | 274 | 297.1667
ACTUAL HOURS | 1522 | 1803 | 700.8333 | 583.0556 | 267.5556 | 297

## PROJECT DETAILS
[Company Name]
Event Management Project Tracker
Company Confidential
[10 empty] | PLANNING | [5 empty] | ACTUALS
PROJECT NAME | PROJECT TYPE | ESTIMATED START | ESTIMATED FINISH | ACTUAL START | ACTUAL FINISH | ESTIMATED WORK | ACTUAL WORK | ESTIMATED DURATION | ACTUAL DURATION | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF | ACCOUNT MANAGER | PROJECT MANAGER | STRATEGY MANAGER | DESIGN SPECIALIST | EVENT STAFF | ADMIN STAFF
A. Datum Corporation | Event strategy development | 2013-06-09 | 2013-08-07 | 2013-06-29 | 2013-09-03 | 200 | 220 | 58 | 64 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7920 | 2640 | 19800 | 0 | 0 | 1320
Adventure Works | Event planning | 2013-06-25 | 2013-07-27 | 2013-07-15 | 2013-08-25 | 400 | 390 | 32 | 40 | 14400 | 24000 | 6000 | 4000 | 0 | 2400 | 14040 | 23400 | 5850 | 3900 | 0 | 2340
Alpine Ski House | Event design | 2013-07-12 | 2013-09-19 | 2013-08-07 | 2013-10-10 | 500 | 500 | 67 | 63 | 18000 | 12000 | 0 | 25000 | 0 | 3000 | 18000 | 12000 | 0 | 25000 | 0 | 3000
Baldwin Museum of Science | Event logistics | 2013-07-30 | 2013-09-28 | 2013-09-14 | 2013-11-13 | 150 | 145 | 58 | 59 | 5400 | 10800 | 0 | 0 | 1200 | 900 | 5220 | 10440 | 0 | 0 | 1160 | 870
Blue Yonder Airlines | Event staffing | 2013-08-11 | 2013-08-21 | 2013-09-14 | 2013-09-25 | 250 | 255 | 10 | 11 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 9180 | 3060 | 0 | 0 | 12240 | 1530
City Power & Light | Event assessment | 2013-08-22 | 2013-10-02 | 2013-09-28 | 2013-10-27 | 300 | 310 | 40 | 29 | 10800 | 7200 | 9000 | 6000 | 0 | 3600 | 11160 | 7440 | 9300 | 6200 | 0 | 3720
Coho Vineyard | Event planning | 2013-09-13 | 2013-09-23 | 2013-10-26 | 2013-10-13 | 500 | 510 | 10 | -13 | 18000 | 30000 | 7500 | 5000 | 0 | 3000 | 18360 | 30600 | 7650 | 5100 | 0 | 3060
Coho Winery | Event logistics | 2013-09-21 | 2013-10-15 | 2013-10-23 | 2013-11-18 | 750 | 790 | 24 | 25 | 27000 | 54000 | 0 | 0 | 6000 | 4500 | 28440 | 56880 | 0 | 0 | 6320 | 4740
Coho Vineyard & Winery | Event assessment | 2013-10-15 | 2013-11-25 | 2013-11-30 | 2014-01-10 | 450 | 430 | 40 | 40 | 16200 | 10800 | 13500 | 9000 | 0 | 5400 | 15480 | 10320 | 12900 | 8600 | 0 | 5160
Contoso, Ltd. | Event staffing | 2013-10-26 | 2013-12-24 | 2013-11-26 | 2014-01-19 | 250 | 235 | 58 | 53 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 8460 | 2820 | 0 | 0 | 11280 | 1410
Contoso Pharmaceuticals | Event planning | 2013-11-17 | 2014-01-15 | 2013-12-28 | 2014-02-26 | 200 | 235 | 58 | 58 | 7200 | 12000 | 3000 | 2000 | 0 | 1200 | 8460 | 14100 | 3525 | 2350 | 0 | 1410
Consolidated Messenger | Event strategy development | 2013-12-03 | 2014-02-02 | 2014-01-14 | 2014-03-02 | 180 | 190 | 59 | 48 | 6480 | 2160 | 16200 | 0 | 0 | 1080 | 6840 | 2280 | 17100 | 0 | 0 | 1140
Fabrikam, Inc. | Event staffing | 2013-06-21 | 2014-01-18 | 2013-08-05 | 2014-03-04 | 250 | 230 | 207 | 209 | 9000 | 3000 | 0 | 0 | 12000 | 1500 | 8280 | 2760 | 0 | 0 | 11040 | 1380
Fourth Coffee | Event logistics | 2013-12-20 | 2014-02-04 | 2014-01-27 | 2014-03-25 | 240 | 225 | 44 | 58 | 8640 | 17280 | 0 | 0 | 1920 | 1440 | 8100 | 16200 | 0 | 0 | 1800 | 1350
Graphic Design Institute | Event design | 2013-12-28 | 2014-03-05 | 2014-01-17 | 2014-04-10 | 320 | 305 | 67 | 83 | 11520 | 7680 | 0 | 16000 | 0 | 1920 | 10980 | 7320 | 0 | 15250 | 0 | 1830
Humongous Insurance | Event planning | 2014-01-04 | 2014-03-06 | 2014-02-03 | 2014-04-06 | 550 | 565 | 62 | 63 | 19800 | 33000 | 8250 | 5500 | 0 | 3300 | 20340 | 33900 | 8475 | 5650 | 0 | 3390
Litware, Inc. | Event design | 2014-01-23 | 2014-03-07 | 2014-03-07 | 2014-04-08 | 350 | 350 | 44 | 31 | 12600 | 8400 | 0 | 17500 | 0 | 2100 | 12600 | 8400 | 0 | 17500 | 0 | 2100
Lucerne Publishing | Event strategy development | 2014-02-05 | 2014-04-17 | 2014-03-07 | 2014-06-03 | 200 | 205 | 72 | 86 | 7200 | 2400 | 18000 | 0 | 0 | 1200 | 7380 | 2460 | 18450 | 0 | 0 | 1230
Margie's Travel | Event planning | 2014-02-15 | 2014-04-30 | 2014-03-26 | 2014-06-09 | 220 | 230 | 75 | 73 | 7920 | 13200 | 3300 | 2200 | 0 | 1320 | 8280 | 13800 | 3450 | 2300 | 0 | 1380
Northwind Traders | Event assessment | 2014-03-17 | 2014-05-25 | 2014-04-29 | 2014-07-01 | 600 | 560 | 68 | 62 | 21600 | 14400 | 18000 | 12000 | 0 | 7200 | 20160 | 13440 | 16800 | 11200 | 0 | 6720
Proseware, Inc. | Event logistics | 2014-03-29 | 2014-05-19 | 2014-05-18 | 2014-06-19 | 525 | 540 | 50 | 31 | 18900 | 37800 | 0 | 0 | 4200 | 3150 | 19440 | 38880 | 0 | 0 | 4320 | 3240
School of Fine Art | Event planning | 2014-04-09 | 2014-04-29 | 2014-05-02 | 2014-06-04 | 180 | 190 | 20 | 32 | 6480 | 10800 | 2700 | 1800 | 0 | 1080 | 6840 | 11400 | 2850 | 1900 | 0 | 1140
TOTAL | [5 empty] | 7565 | 7610 | 1223 | 1205